## Sheet1
FlyAway Agile Project Plan
Task Name | Priority | Owner | Start Date | End Date | Status
Sprint #1: Analysis and Design
Making Sprint Plan | High | Pravallika | 2022-04-15 | 2022-04-17 | Done
Specification document | Low | Pravallika | 2022-04-16 | 2022-04-18 | Done
Prepare Algorithm | High | Pravallika | 2022-04-17 | 2022-04-18 | Done
Create Flow Chart | Medium | Pravallika | 2022-04-17 | 2022-04-18 | Done
Setup Git Repository | High | Pravallika | 2022-04-18 | 2022-04-18 | Done
Sprint #2: Develop and Execute
Setup Environment | Medium | Pravallika | 2022-04-18 | 2002-03-30 | Done
Code Html and J | High | Pravallika | 2022-03-28 | 2002-03-30 | Done
Code to delete file | High | Pravallika | 2022-03-29 | 2002-03-31 | Done
Code to search file | High | Pravallika | 2022-03-29 | 2002-04-01 | Done
Code to Navigate and close Application | Medium | Pravallika | 2022-03-31 | 2002-04-01 | Done
Sprint #3: Test, Fix & Install
Test the Application | High | Pravallika | 2022-04-19 | 2022-04-25 | Done
Fix issues | High | Pravallika | 2022-04-19 | 2022-04-27 | Done
Regression Test | Low | Pravallika | 2022-04-22 | 2022-04-27 | Done
Upload to Git Repository | Medium | Pravallika | 2022-04-23 | 2022-04-27 | Done
Submit Project | High | Pravallika | 2022-04-24 | 2022-04-27 | Done